***Mosaix IMPACT Map of Plan Module***

**Assess:**

**Problem Behavior:**

* High retail access to alcohol for minors.

**Plan:**

**Goal:**

* Reduce retail access of alcohol to minor by 3% with by June 30, 2016.

**Objective:**

* Reduce the illegal sales of alcohol to minors within our community alcohol retail stores as measured by the Alcohol Purchasing Survey.

**Program:**

1. Compliance Checks
2. Training program from staff at liquor stores.

**Activities:**

* **Compliance Checks:**
	+ Recruit and train students for compliance checks.
	+ Complete compliance checks at all alcohol retail establishments in the jurisdiction.
	+ Information dissemination of results measured by the Alcohol Purchasing Survey.

**Participants/Reoccurring group:**

* **Compliance Checks:**
* Recruit and train students for compliance checks.
	+ Senior SADD members were recruited and trained.
* Complete compliance checks at all alcohol retail establishments in the jurisdiction.
	+ Each student was paired with a police officer and completed the checks.
* Information dissemination of the results measured by the Alcohol Purchasing Survey.
	+ Coordinator disseminated information gathered from compliance checks.